## Sheet
ID | Issue Type | State | Ceated By | Currently Assigned To | Issue Title | Verified on Software Version | Verification result | Verification Assigned
811766 | Working Issue | (Verified) | Mihai Ianos (mihai.ianos) | Emanuel Jivan (emanuel.jivan) | [TST] Encryption issue in Vector stack
811786 | Change Request | (Reviewed) | Mihai Ianos (mihai.ianos) | Septimiu Vintila (septimiu.vintila) | [R01.0] Global Time Sync Mechanism
811861 | Change Request | (To Be Verified) | Mihai Ianos (mihai.ianos) | Mircea Teodorescu (mircea.teodorescu) | [R01.0] Implement triggering of two tensioning profiles (CIL, PRE, NVP)
811862 | Change Request | (To Be Verified) | Mihai Ianos (mihai.ianos) | Mircea Teodorescu (mircea.teodorescu) | [R01.0] Implement triggering of release profile (CIL, SFR, NVP)
811911 | Change Request | (To Be Verified) | Roberto Cristoi (roberto.cristoi) | Mircea Teodorescu (mircea.teodorescu) | [B3.1] Positive response to unknown session ( 10 04 )
811976 | Change Request | (To Be Verified) | Mihai Ianos (mihai.ianos) | Mircea Teodorescu (mircea.teodorescu) | [R01.0] Implement Autoliv internal UDS
811993 | Change Request | (Verified) | Roberto Cristoi (roberto.cristoi) | Emanuel Jivan (emanuel.jivan) | [B3.1] Flashing fails after hard reset
812102 | Change Request | (Implemented) | Mihai Ianos (mihai.ianos) | Emanuel Jivan (emanuel.jivan) | [R01.0] Software Build
811787 | Change Request | (Reviewed) | Mihai Ianos (mihai.ianos) | Roberto Cristoi (roberto.cristoi) | [R01.0] Integrate FBL SIP 1.2.2.0
811788 | Change Request | (Reviewed) | Mihai Ianos (mihai.ianos) | Roberto Cristoi (roberto.cristoi) | [R01.0] Integrate HSM SIP 1.2.2.0
811789 | Change Request | (Reviewed) | Mihai Ianos (mihai.ianos) | Emanuel Jivan (emanuel.jivan) | [R01.0] Integrate MSR SIP 1.2.2.0
812140 | Working Issue | (Reviewed) | Victor Ursache (victor.ursache) | Mihai Ianos (mihai.ianos) | [TST] Wrong value implemented for high limit operating voltage.
812187 | Working Issue | (Reviewed) | Victor Ursache (victor.ursache) | Mihai Ianos (mihai.ianos) | [TST] Toggle is NOT active for 'RBTM_FL_Tgl_ST3' when frame active.
812195 | Working Issue | (Reviewed) | Sebastian Masone (sebastian.masone) | Andreea Negrea (andreea.negrea) | [TST] Tensioning profile is not inhibited if Impact_RO_typeX_ST3 signal is set to 1
812310 | Working Issue | (Reviewed) | Emanuel Jivan (emanuel.jivan) | Roberto Cristoi (roberto.cristoi) | [FBL] Change encryption key and IV
812494 | Working Issue | (Reviewed) | Stefan Dominte (stefan.dominte) | Mihai Ianos (mihai.ianos) | [R01.1] CIL integration test code findings
812554 | Working Issue | (Reviewed) | Jenkins Server 01 (Jenkins01) | Alexandru Paval (alexandru.paval) | [Diag]: COM Control Service EnableRxAndDisableTx does not shut down the ECU Sp
812609 | Change Request | (Reviewed) | Mihai Ianos (mihai.ianos) | Stefan Dominte (stefan.dominte) | [R01.1] Tensioning configuration validity precheck
812610 | Change Request | (Reviewed) | Mihai Ianos (mihai.ianos) | Mirela Obada (mirela.obada) | [R01.1] Tensioning abortion from "Impact_X/Y" signals
812611 | Change Request | (Reviewed) | Mihai Ianos (mihai.ianos) | Emanuel Jivan (emanuel.jivan) | [R01.0] Fix BROP findings
812640 | Change Request | (Reviewed) | Mihai Ianos (mihai.ianos) | Alexandru Paval (alexandru.paval) | [R01.1] FBL fingerprint implementation
812736 | Change Request | (Reviewed) | Mihai Ianos (mihai.ianos) | Mihai Ianos (mihai.ianos) | [R01.1] Software identification update
812738 | Change Request | (Reviewed) | Mihai Ianos (mihai.ianos) | Septimiu Vintila (septimiu.vintila) | [R01.0] RTM integration