## Sheet1
Task Mode | Task Name | Duration | Start | Finish | Predecessors | Resource Names | % Complete | State | UID | Task Template
Auto Scheduled | TestProject | 16 days? | Wed 27.01.21 | Wed 17.02.21 |  |  | 0%
Auto Scheduled | [Training][P10] Another Test issue | 13 days? | Wed 27.01.21 | Fri 12.02.21 |  |  | 0% | (Implemented) | 805362
Auto Scheduled | [Training][P10] Another Test issue - Analysis | 2 day | Thu 28.01.21 | Thu 28.01.21 |  | Dan Dustinta | 100% |  |  | Analysis
Auto Scheduled | [Training][P10] Another Test issue - Requirements Update/Traceability | 3 day | Fri 29.01.21 | Fri 29.01.21 |  | Dan Dustinta | 100% |  |  | Requirements Update/Traceability
Auto Scheduled | [Training][P10] Another Test issue - Requirements Review | 4 day | Mon 08.02.21 | Mon 08.02.21 |  | Dan Dustinta | 100% |  |  | Requirements Review
Auto Scheduled | [Training][P10] Another Test issue - Architecture Specification | 5 day | Tue 09.02.21 | Tue 09.02.21 |  | Dan Dustinta | 100% |  |  | Architecture Specification
Auto Scheduled | [Training][P10] Another Test issue - Architecture Specification Review | 6 day | Wed 10.02.21 | Wed 10.02.21 |  | Dan Dustinta | 100% |  |  | Architecture Specification Review
Auto Scheduled | [Training][P10] Another Test issue - Design Specification | 7 day | Thu 11.02.21 | Fri 12.02.21 |  | Dan Dustinta | 100% |  |  | Design Specification
Auto Scheduled | [Training][P10] Another Test issue - Design Specification Review | 8 day | Fri 05.02.21 | Fri 05.02.21 |  | Dan Dustinta | 100% |  |  | Design Specification Review
Auto Scheduled | [Training][P10] Another Test issue - Code Implementation | 9 day | Wed 27.01.21 | Wed 27.01.21 |  | Dan Dustinta | 100% |  |  | Code Implementation
Auto Scheduled | [Training][P10] Another Test issue - QAC/Code Metrics Verification | 10 day | Thu 28.01.21 | Mon 01.02.21 |  | Dan Dustinta | 100% |  |  | QAC/Code Metrics Verification
Manually Scheduled | [Training][P10] Another Test issue - Code Review | 11 day |  |  |  | Dan Dustinta | 100% |  |  | Code Review
Auto Scheduled | [Training][P10] Another Test issue - Unit Test Specification | 12 day | Fri 29.01.21 | Fri 29.01.21 |  | Dan Dustinta | 100% |  |  | Unit Test Specification
Auto Scheduled | [Training][P10] Another Test issue - Unit Test Specification Review | 13 day | Mon 01.02.21 | Mon 01.02.21 |  | Dan Dustinta | 100% |  |  | Unit Test Specification Review
Auto Scheduled | [Training][P10] Another Test issue - Integration Test Specification | 14 day | Tue 02.02.21 | Tue 02.02.21 |  | Dan Dustinta | 100% |  |  | Integration Test Specification
Auto Scheduled | [Training][P10] Another Test issue - Integration Test Specification Review | 15 day | Wed 03.02.21 | Wed 03.02.21 |  | Dan Dustinta | 100% |  |  | Integration Test Specification Review